## Schedule
Week | Date |  | Development Plan | Testing/Demonstration
5 | February | 10 | -Research - Database - Managing user information - Android Studio | N/A
6 |  | 17 | - Create skeleton website - Populate with information about parties - Create links to allow for navigation | - Customer should be able to view party package details - Customer should be able to naviagate website
7 |  | 24 | Research and create a scheduling algorithm that fits with our set requirements, that allows for parties to be fit as efficiently as possible without any errors | - Enter dummy information into algorithm and confirm that it minimizes errors while searching for efficiency - Include tests for edge cases
8 | March | 2
|  | 9 | Create scheduler page on website that uses the algorithm created in the previous weeks. | - Using website, test algorithm again, and confirm that it works as expected with test cases created in previous weeks
9 |  | 16 | Edit scheduler pages to allow for collection of required information. This information should be saved to a database securely, and without loss. The party should not continue booking if information is lost. | - Using dumby information create a party and finish booking it up to this step. Enter in information and confirm it is saved in the database
10 |  | 23 | Add payment options. A party may not be booked without payment, edit the previous step so that the party is not finalized without payment. | - Using PayPal's sandbox features, test this by booking a party and paying for it. Test both with payments and without payments to confirm a party is booked as expected
11 |  | 30 | 1. Begin creating a staff portal 2. Add feature for exporting parties into a pdf form to be printed for each weekend. | Up to this point there was no way for a staff member to authenticate. Test logging in as a staff member. Using fake party information test exporting party info.
12 | April | 6 | Add staff permissions. Add all features that staff members should have | Test all permissions of staff member. Such as adding and removing parties, editing party details, moving a party, and bypassing payments
13 |  | 13
14 |  | 20 | 1. Unit testing 2. Create android webview app. | Testing everything. Making sure that everything is working as expected and everything is ready for prime time
15 |  | 27 | Final touches on website and app. Final conversations with Paramount to ensure it is what they expected
Final | May | 4 | Website goes live

## Gantt Chart
| February |  |  | March |  |  |  |  | April
| 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
Research
Skeleton Website
Scheduling Algorithm
Scheduler Page
Payment Options
Staff Portal
Staff Permissions
Exporting Parties
Testing
Android App
Finalization